## Ark1
| Start Date | Total Days | Days complete | Days Remaining | Task | Lead role | Start | End | Lofthus frukt og saft website development project
Planning | 2019-11-11 | 5 | 5 | 0 | Planning | Project Manager | 2019-11-11 | 2019-11-16 | Start 11.11.2019
Marketing research | 2019-11-13 | 3 | 3 | 0 | Marketing research | Digital Marketer | 2019-11-13 | 2019-11-16 | End 29.12.2019
Design | 2019-11-15 | 10 | 2 | 8 | Design | Graphic Designer | 2019-11-15 | 2019-11-25
Style tile | 2019-11-19 | 13 | 0 | 13 | Style tile | Graphic Designer | 2019-11-19 | 2019-12-03
Web layout | 2019-11-24 | 12 | 0 | 12 | Web layout | Graphic Designer | 2019-11-24 | 2019-12-12
Develop | 2019-12-06 | 25 | 0 | 25 | Develop | Frontend dev | 2019-12-06 | 2019-12-28
Set up homepage | 2019-12-07 | 4 | 0 | 4 | Set up homepage | Frontend dev | 2019-12-07 | 2019-12-11
Set up about page | 2019-12-12 | 4 | 0 | 4 | Set up about page | Frontend dev | 2019-12-12 | 2019-12-16
Set up contact page | 2019-12-14 | 4 | 0 | 4 | Set up contact page | Frontend dev | 2019-12-14 | 2019-12-18
Set up Products page | 2019-12-16 | 4 | 0 | 4 | Set up Products page | Frontend dev | 2019-12-16 | 2019-12-20
Get the design right | 2019-12-18 | 5 | 0 | 5 | Get the design right and copyright | Frontend dev / Copywriter/content specialist | 2019-12-18 | 2019-12-22
Make it responsive | 2019-12-20 | 4 | 0 | 4 | Make it responsive | Frontend dev | 2019-12-20 | 2019-12-24
Testing | 2019-12-22 | 5 | 0 | 5 | Testing | Frontend dev | 2019-12-22 | 2019-12-27
Launch | 2019-12-27 | 2 | 0 | 2 | Launch | Frontend dev | 2019-12-27 | 2019-12-29
Formulas:
Days complete = IF(TODAY()-[Start Date]>[Total Days],[Total Days],IF(TODAY()-[Start Date]<0,0,TODAY()-[Start Date]))